Wholesale Parts E-Commerce Platform

MVP Development Plan & Execution Guide

Project Timeline: 4 Weeks

Budget: ~$25-40/month

Target Scale: 15,000 products | 4,000 users

Table of Contents

[Right-click and select "Update Field" to generate table of contents in Microsoft Word]

# 📋 Executive Summary

## Business Objectives

Enable efficient product search for 15,000+ mechanical parts

Streamline wholesale order inquiries through WhatsApp automation

Provide real-time analytics for admin decision-making

Maintain data synchronization with client's existing PHP database

## Success Metrics

| Metric | Target | Measurement |
| --- | --- | --- |
| Search Response Time | <500ms | Lighthouse Performance |
| System Uptime | 95%+ | Vercel Analytics |
| WhatsApp Delivery | <30 seconds | n8n Execution Logs |
| Database Sync Accuracy | 100% | Daily Verification Logs |
| Mobile Responsiveness | 100% | Cross-device Testing |

# 🏗️ System Architecture

## High-Level Architecture

The system follows a modern 3-tier architecture:

Presentation Layer: Next.js 15 app hosted on Vercel (free tier)

Application Layer: Supabase (PostgreSQL + Auth + Real-time)

Integration Layer: n8n workflows for automation and syncing

Data Source: Clients existing PHP database (read-only)

## Technology Stack Rationale

| Component | Technology | Cost/Month | Justification |
| --- | --- | --- | --- |
| Frontend | Next.js 15 | $0 | Server components, SEO, optimizations |
| Hosting | Vercel | $0 | Zero-config deployment, SSL, edge CDN |
| Database | Supabase PostgreSQL | $0 | Millions of rows, full-text search |
| Authentication | Supabase Auth | $0 | Production-ready, RLS integration |
| Automation | n8n Cloud | $20 | Team expertise, visual workflows |
| Messaging | Twilio WhatsApp | ~$5 | Official API, reliable delivery |
| TOTAL |  | ~$25-30 | Scales to 10,000+ users |

# 📅 Development Phases Overview

## Timeline Summary

| Week | Phase | Focus | Key Deliverables |
| --- | --- | --- | --- |
| 1-2 | Phase 1 | Foundation & Infrastructure | Database, Auth, Search, Manual Sync |
| 3 | Phase 2 | Core Features | Cart, Orders, WhatsApp, Admin Dashboard |
| 4 | Phase 3 | Production Readiness | Auto Sync, Security, Monitoring, Deployment |

# PHASE 1: Foundation & Infrastructure

Week 1-2 (Days 1-14)

## 🎯 Phase Objective

Build the technical foundation: database, authentication, basic product browsing, and search capabilities.

## 📦 Key Deliverables

✅ Fully configured Supabase project with production schema

✅ Working authentication system (signup/login)

✅ Product listing page with pagination

✅ Advanced search functionality (exact, fuzzy, category-based)

✅ Manual n8n workflow for database synchronization

### 1.1 Database Setup & Schema Design

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Create Supabase project & configure | Backend Dev | 2 hours | Critical |
| Design and implement database schema | Backend Dev | 4 hours | Critical |
| Create database indexes for performance | Backend Dev | 2 hours | High |
| Set up Row Level Security (RLS) policies | Backend Dev | 3 hours | High |
| Seed database with sample products | Backend Dev | 1 hour | Medium |

#### Database Schema Overview

Core Tables:

products: Main product catalog - Stores SKU, name, description, category, brand, specifications, full-text search vectors, stock status, sync timestamps

profiles: User information (extends Supabase Auth) - Stores company name, phone, address, role (customer/admin)

cart_items: Shopping cart (temporary storage) - Stores user ID, product ID, quantity, cleared after order creation

orders: Order inquiries (not payment orders) - Stores order number, items snapshot, customer info, status, communication tracking

daily_analytics: Pre-aggregated statistics - Stores daily totals, top products, unique users, generated by n8n at 1 AM

sync_logs: Synchronization audit trail - Stores sync status, products synced, errors for debugging and monitoring

#### Search Optimization Strategy

Three-Tier Search Architecture:

Tier 1: Exact Match (Weight: 1.0): Direct SKU lookup using B-tree index. Returns in <10ms for exact matches. Example: User searches "BRK-001" → exact product

Tier 2: Full-Text Search (Weight: 0.8-0.5): PostgreSQL tsvector with ts_rank scoring. Handles stemming (brake → braking), typos, multi-word queries. Example: "hydraulic brake system" → ranked results. Target: <300ms

Tier 3: Fuzzy Matching (Weight: 0.3): ILIKE pattern matching on category/brand. Catches related products and similar categories. Example: "brake" → all brake-related products. Target: <500ms

#### Performance Targets

| Search Type | Target Time | Implementation |
| --- | --- | --- |
| Exact SKU Match | <50ms | B-tree index on SKU column |
| Full-Text Search | <300ms | GIN index on search vector |
| Fuzzy Match | <500ms | ILIKE pattern with category/brand indexes |

#### Security: Row Level Security (RLS) Policies

Products Table: Public read access (anonymous browsing), Admin-only write access

Cart Table: Users can only view/modify their own cart, Isolation prevents data leakage

Orders Table: Users view only their own orders, Admins view all orders, Users can create but not modify after creation

Analytics Table: Admin-only access, Prevents business intelligence leakage

### 1.2 Authentication System

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Configure Supabase Auth settings | Backend Dev | 1 hour | Critical |
| Build login page UI | Frontend Dev | 2 hours | Critical |
| Build signup page UI | Frontend Dev | 3 hours | Critical |
| Implement client-side auth hooks | Frontend Dev | 2 hours | High |
| Set up middleware for route protection | Backend Dev | 2 hours | High |
| Test auth flow (signup → verify → login) | QA | 1 hour | High |

#### Route Protection Strategy

Public Routes (No Auth Required): Homepage, product catalog, product details, login/signup pages

Protected Customer Routes (Auth Required): Cart, order history, user profile

Protected Admin Routes (Auth + Admin Role): Dashboard, product management, all orders, analytics

Implementation: Next.js middleware checks JWT token and user role before rendering protected routes.

### 1.3 Next.js Application Setup

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Initialize Next.js 15 project | Frontend Dev | 1 hour | Critical |
| Install dependencies (Supabase, UI) | Frontend Dev | 1 hour | Critical |
| Set up project folder structure | Frontend Dev | 2 hours | High |
| Configure TypeScript & ESLint | Frontend Dev | 1 hour | Medium |
| Create reusable UI components | Frontend Dev | 4 hours | High |
| Set up Tailwind CSS & design system | Frontend Dev | 2 hours | Medium |

#### Key Architectural Decisions

Server Components by Default: Reduces JavaScript bundle sent to client, improves initial page load time, better SEO (fully rendered HTML)

Server Actions for Mutations: Type-safe data mutations, automatic revalidation, no need for separate API routes

Route Groups for Organization: (public) - no auth, (customer) - requires login, (admin) - requires admin role. Groups dont affect URL structure

Environment Variables Strategy: Public vars: NEXT_PUBLIC_SUPABASE_URL, NEXT_PUBLIC_SUPABASE_ANON_KEY. Private (server-only): SUPABASE_SERVICE_ROLE_KEY

### 1.4 Product Listing & Search Implementation

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Create search database function | Backend Dev | 3 hours | Critical |
| Build product listing page | Frontend Dev | 4 hours | Critical |
| Implement search bar component | Frontend Dev | 3 hours | Critical |
| Add category filtering | Frontend Dev | 2 hours | High |
| Implement pagination | Frontend Dev | 2 hours | High |
| Add loading states & error handling | Frontend Dev | 2 hours | Medium |

#### Search Algorithm Details

Input Processing:

Trim whitespace

Convert to lowercase for comparison

Detect if input matches SKU pattern (e.g., BRK-001)

Ranking Strategy:

Final Score = (Match Type Weight) × (Stock Bonus) × (Text Rank)

Match Type Weights:

• Exact SKU: 1.0

• Full-text: 0.5-0.8 (ts_rank score)

• Fuzzy: 0.3

Stock Bonus:

• In stock: 1.0

• Out of stock: 0.5

Result Grouping:

Exact Matches: shown first (highlighted border)

Relevant Results: shown next (best text matches)

Related Products: shown last (category/brand matches)

#### Performance Optimization

Database Level:

GIN index on search vector: ~100x faster than LIKE queries

Materialized view for frequently searched categories (future)

Query result caching (future phase)

Application Level:

Debounce search input (300ms) - reduces API calls

Server-side rendering for initial load (instant results)

Optimistic UI updates for better perceived performance

Frontend Level:

Lazy load images with Next.js <Image> component

Virtual scrolling for large result sets (future)

Skeleton loaders during search

### 1.5 Manual Database Sync Workflow (n8n)

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Set up n8n Cloud account | Integration Dev | 1 hour | Critical |
| Create manual sync workflow | Integration Dev | 4 hours | Critical |
| Map PHP API fields to Supabase | Integration Dev | 2 hours | High |
| Add error handling & logging | Integration Dev | 2 hours | High |
| Test with sample data from client | Integration Dev | 2 hours | High |
| Document sync process | Integration Dev | 1 hour | Medium |

#### n8n Workflow Design: Manual Database Sync

Workflow Steps:

1. Manual Trigger Button: Developer clicks "Execute Workflow"

2. HTTP Request Node: GET /api/products?limit=1000 from Clients PHP API

3. Code Node (Transform Data): Map PHP fields → Supabase fields, detect new vs existing, flag stock changes

4. Split Into Batches: Process 100 products at a time (prevents memory issues)

5. Loop Over Batches: For each batch, UPSERT to Supabase (ON CONFLICT external_id), wait 1s for rate limiting

6. Supabase Node (Log Results): INSERT INTO sync_logs (success/failure, counts, errors)

7. IF Node: Check for errors, send email alert if any failures

#### Error Handling Strategy

Network Errors: Retry 3 times with exponential backoff (1s, 2s, 4s), Log failure details to sync_logs, Send alert email to admin

Data Validation Errors: Skip invalid products (log SKU and reason), Continue processing valid products, Generate error report at end

Rate Limiting: Wait 1 second between batches, If 429 error received, wait 60 seconds and retry

#### Success Criteria for Phase 1

☐ Database schema created and tested

☐ All RLS policies implemented and verified

☐ Users can sign up and log in successfully

☐ Product listing page displays 20+ products

☐ Search returns results in <500ms

☐ Manual sync workflow successfully syncs 100+ products

☐ All protected routes require authentication

☐ Mobile-responsive UI (tested on 3 devices)

# PHASE 2: Core Features

Week 3 (Days 15-21)

## 🎯 Phase Objective

Implement shopping cart, order inquiry system, WhatsApp notifications, and basic admin dashboard.

## 📦 Key Deliverables

✅ Fully functional shopping cart with add/remove/update

✅ Order creation flow with customer info capture

✅ Automated WhatsApp notifications via n8n

✅ Admin dashboard with sales analytics

### 2.1 Shopping Cart System

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Create cart UI components | Frontend Dev | 4 hours | Critical |
| Implement add to cart functionality | Frontend Dev | 3 hours | Critical |
| Build cart page with item management | Frontend Dev | 4 hours | Critical |
| Add quantity update logic | Frontend Dev | 2 hours | High |
| Implement remove from cart | Frontend Dev | 1 hour | High |
| Add cart badge to header | Frontend Dev | 1 hour | Medium |

#### Cart State Management

Approach: Server-driven state with optimistic updates

Why Server-driven?

Single source of truth (database)

No state sync issues across tabs

Cart persists across sessions

Works with server components

Optimistic Updates:

User clicks "Add" → UI updates instantly → API call in background

↓ If success: confirmed

↓ If error: rollback UI + show error toast

### 2.2 Order Creation Flow

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Design order creation UI | Frontend Dev | 3 hours | Critical |
| Build customer info confirmation form | Frontend Dev | 3 hours | Critical |
| Implement order submission logic | Backend Dev | 4 hours | Critical |
| Create order confirmation page | Frontend Dev | 2 hours | High |
| Set up database webhook for orders | Backend Dev | 2 hours | High |
| Test end-to-end order flow | QA | 2 hours | High |

#### Order Creation Process

1. User reviews cart and clicks "Place Order"

2. Redirect to /checkout

3. Display confirmation form: company name, phone, special instructions

4. Validate form inputs

5. Server Action: createOrder()

6.   • Fetch cart items + product details

7.   • Fetch user profile

8.   • Generate order number (ORD-2024-00001)

9.   • Create order record (with items snapshot)

10.   • Clear users cart

11. Database trigger fires → Supabase webhook → n8n

12. WhatsApp notification sent to company

13. Redirect to /orders/[orderId] confirmation page

#### Order Data Snapshot Strategy

Why Snapshot?

Products may change price/name later

Order should reflect prices/names at time of order

Audit trail for what customer actually ordered

Snapshot includes:

Product ID, SKU, Name (at order time)

Price (at order time)

Quantity ordered

Image URL

Customer name, company, phone, email

### 2.3 WhatsApp Notification Workflow (n8n)

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Set up Twilio account & sandbox | Integration Dev | 1 hour | Critical |
| Create n8n webhook trigger | Integration Dev | 1 hour | Critical |
| Build WhatsApp notification workflow | Integration Dev | 4 hours | Critical |
| Design message template | Integration Dev | 2 hours | High |
| Test with sample orders | Integration Dev | 2 hours | High |
| Add fallback notifications (email) | Integration Dev | 2 hours | Medium |

#### n8n Workflow: WhatsApp Order Notification

1. Webhook Trigger: Receives POST from Supabase (order data)

2. Extract Order Data (Code Node): Parse order number, customer info, items list

3. Supabase Node: Fetch full product details (if needed)

4. Code Node (Format Message): Create WhatsApp message template

5. HTTP Request Node: POST to Twilio WhatsApp API

6.   → Success: Update order.whatsapp_sent_at timestamp

7.   → Failure: Send email alert, log error

#### WhatsApp Setup Options

| Option | Setup Time | Cost | Recommendation |
| --- | --- | --- | --- |
| Twilio | 30 minutes | $0.005/msg | ✅ Recommended for MVP |
| WhatsApp Business API | 2-3 days | Variable | For production scale |
| WAHA (Self-hosted) | 2 hours | Free | Not recommended (ToS risk) |

#### Message Template Best Practices

Structure:

Header: Emoji + "New Order Received"

Order Info: Number, timestamp

Customer Info: Name, company, phone

Items List: Product name, SKU, quantity

Special Notes: Customer instructions

Action Link: Direct link to order details

Character Limit: Keep under 1600 characters (WhatsApp limit)

### 2.4 Admin Dashboard (Basic Analytics)

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Design dashboard layout | Frontend Dev | 3 hours | High |
| Implement key metrics cards | Frontend Dev | 3 hours | High |
| Build recent orders table | Frontend Dev | 3 hours | High |
| Create top products widget | Frontend Dev | 2 hours | Medium |
| Add basic charts (optional) | Frontend Dev | 3 hours | Low |
| Implement admin order management | Frontend Dev | 4 hours | High |

#### Dashboard Components

Metric Cards: Todays orders, new customers, pending orders

Top Products Widget: Best-selling products (last 7 days) with order counts

Recent Orders Table: Latest orders with status, customer name, item count

Order Management: Update status, add notes, mark as contacted, resend WhatsApp

#### Admin Order Management Features

Order Actions:

✅ View full order details

✅ Update order status (Pending → Contacted → Processing → Completed)

✅ Add admin notes

✅ Mark as "Contacted" with timestamp

✅ Resend WhatsApp notification (if failed)

Order Status Workflow:

Pending → Contacted → Processing → Completed

↓                                    ↑

└────────→ Cancelled ───────────────┘

#### Success Criteria for Phase 2

☐ Users can add products to cart

☐ Cart persists across sessions

☐ Users can place orders successfully

☐ Orders appear in admin dashboard within 1 minute

☐ WhatsApp notifications delivered within 30 seconds

☐ Admin can view and update order status

☐ Top products widget shows accurate data

☐ All features work on mobile devices

# PHASE 3: Production Readiness & Polish

Week 4 (Days 22-28)

## 🎯 Phase Objective

Automate workflows, implement comprehensive security, add monitoring, and deploy to production.

## 📦 Key Deliverables

✅ Automated database sync (scheduled every 30 minutes)

✅ Comprehensive RLS testing and security audit

✅ Error handling and logging system

✅ Production deployment on Vercel

✅ Monitoring and alerting setup

### 3.1 Automated Database Sync

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Convert manual to scheduled workflow | Integration Dev | 2 hours | Critical |
| Set up cron schedule (every 30 min) | Integration Dev | 1 hour | Critical |
| Add incremental sync logic | Integration Dev | 4 hours | High |
| Implement conflict resolution | Integration Dev | 3 hours | High |
| Add sync monitoring dashboard | Integration Dev | 2 hours | Medium |
| Create sync failure alerts | Integration Dev | 2 hours | High |

#### Incremental Sync Strategy

Why Incremental?

Reduces API load on clients server

Faster sync times (seconds vs minutes)

Less bandwidth usage

Lower risk of timeout errors

Implementation:

Track last successful sync timestamp

Request only products updated since that timestamp

Compare against existing data to detect changes

Apply only necessary updates

Conflict Resolution: Clients database is source of truth. Always use data from PHP API. Track all overrides for audit.

#### Alert Triggers

⚠️ Sync fails 3 times in a row

⚠️ No successful sync in last 2 hours

⚠️ More than 50 products fail validation

⚠️ Sync duration exceeds 5 minutes

### 3.2 Security Hardening & RLS Testing

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Audit all RLS policies | Backend Dev | 3 hours | Critical |
| Test RLS with different user roles | QA | 4 hours | Critical |
| Implement API rate limiting | Backend Dev | 2 hours | High |
| Add CSRF protection | Backend Dev | 2 hours | High |
| Security headers configuration | Backend Dev | 1 hour | High |
| Penetration testing (basic) | QA | 3 hours | Medium |

#### Security Checklist

Authentication Security:

☐ Password minimum 6 characters enforced

☐ Email verification enabled (optional for MVP)

☐ Session tokens expire after 7 days

☐ Logout clears all session data

API Security:

☐ Rate limiting: 100 requests/minute per IP

☐ CORS configured for allowed domains only

☐ API keys stored in environment variables

☐ No sensitive data in URL parameters

Database Security:

☐ Service role key never exposed to client

☐ All tables have RLS enabled

☐ Policies tested with automated scripts

☐ No SQL injection vulnerabilities

Frontend Security:

☐ HTTPS enforced in production

☐ Security headers configured (CSP, X-Frame-Options)

☐ User input sanitized before display

☐ No sensitive data in localStorage

### 3.3 Error Handling & Logging

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Implement global error boundary | Frontend Dev | 2 hours | High |
| Add error logging service | Backend Dev | 3 hours | High |
| Create error notification system | Backend Dev | 2 hours | Medium |
| Add user-friendly error messages | Frontend Dev | 2 hours | High |
| Set up error monitoring dashboard | Backend Dev | 2 hours | Medium |

#### Error Categories

| Category | Response | Logging | Example |
| --- | --- | --- | --- |
| User Errors (4xx) | Friendly message | Not logged | Product not found |
| System Errors (5xx) | Generic message | Log + alert | Database connection failed |
| Third-Party | Retry 3x | Log after failures | WhatsApp API timeout |

#### Log Levels

ERROR: Critical failures (system errors, API failures) - Stored 90 days

WARN: Important but recoverable (validation failures, timeouts) - Stored 30 days

INFO: Normal operations (successful orders, syncs) - Stored 7 days

DEBUG: Development troubleshooting (search queries) - Not stored in production

### 3.4 Production Deployment

#### Tasks Breakdown

| Task | Owner | Duration | Priority |
| --- | --- | --- | --- |
| Configure production env variables | DevOps | 1 hour | Critical |
| Set up Vercel project | DevOps | 1 hour | Critical |
| Configure custom domain (optional) | DevOps | 2 hours | High |
| Run production build test | QA | 1 hour | Critical |
| Deploy to Vercel production | DevOps | 1 hour | Critical |
| Verify deployment | QA | 2 hours | Critical |
| Set up monitoring alerts | DevOps | 2 hours | High |

#### Pre-Deployment Checklist

Code Quality:

☐ All TypeScript errors resolved

☐ No console.log statements in production

☐ All environment variables documented

☐ Build passes without warnings

Performance:

☐ Lighthouse score >90 (mobile)

☐ First Contentful Paint <2s

☐ Time to Interactive <3s

☐ Images optimized with Next.js Image

Security:

☐ All API keys in environment variables

☐ HTTPS enforced

☐ Security headers configured

☐ RLS policies active

Functionality:

☐ All features tested on staging

☐ Search works correctly

☐ Orders create successfully

☐ WhatsApp notifications send

☐ Admin dashboard loads

#### Post-Deployment Monitoring

Metrics to Monitor:

✅ Response time (target: <1s for 95% of requests)

✅ Error rate (target: <0.1%)

✅ Uptime (target: 99.5%)

✅ Database connections (check for leaks)

✅ n8n workflow success rate

Monitoring Tools:

Vercel Analytics (built-in)

Supabase Dashboard (database metrics)

n8n Execution History

Uptime monitoring (UptimeRobot - free)

#### Success Criteria for Phase 3

☐ Database syncs automatically every 30 minutes

☐ All RLS policies tested and passing

☐ Error handling implemented across application

☐ Production deployment successful

☐ Monitoring alerts configured

☐ Zero critical errors in first 24 hours

☐ All user flows work in production

☐ Performance targets met (Lighthouse >90)

# 💰 Cost Breakdown

## Monthly Operating Costs

| Service | Tier | Monthly Cost | Annual Cost |
| --- | --- | --- | --- |
| Vercel Hosting | Hobby | $0 | $0 |
| Supabase | Free | $0 | $0 |
| n8n Cloud | Starter | $20 | $240 |
| Twilio WhatsApp | Pay-as-you-go | ~$5 | ~$60 |
| Domain (optional) | - | ~$1 | ~$12 |
| TOTAL |  | $26/month | $312/year |

## Scaling Cost Projections

| User Count | Vercel | Supabase | n8n | Total/Month |
| --- | --- | --- | --- | --- |
| 4,000 (Current) | $0 | $0 | $20 | $26 |
| 10,000 | $0 | $25 (Pro) | $20 | $51 |
| 50,000 | $20 (Pro) | $25 (Pro) | $50 (Pro) | $95 |

# 🚨 Risk Management

## Technical Risks

| Risk | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| Clients API unreliable | High | Medium | Retry logic, caching, alerts |
| Database sync failures | High | Low | Automated monitoring, manual sync option |
| WhatsApp delivery fails | Medium | Low | Email fallback, retry queue |
| Vercel rate limiting | Medium | Low | Optimize queries, caching, monitor usage |
| Search performance issues | Medium | Medium | Database indexing, optimization |

# 🎉 Success Metrics (Post-Launch)

## Week 1 Targets

100+ user signups

500+ product searches

50+ orders placed

99%+ uptime

## Month 1 Targets

500+ active users

2,000+ orders placed

<0.1% error rate

Positive user feedback

## Quarter 1 Targets

2,000+ active users

10,000+ orders placed

99.5%+ uptime

ROI positive (revenue > costs)

# ✅ Final Pre-Launch Checklist

## Functionality

☐ Users can sign up and log in

☐ Search returns accurate results

☐ Cart adds/removes items correctly

☐ Orders create successfully

☐ WhatsApp notifications send within 30 seconds

☐ Admin can view and manage orders

☐ Database syncs every 30 minutes

☐ All features work on mobile

## Performance

☐ Lighthouse score >90

☐ Search completes in <500ms

☐ Pages load in <2 seconds

☐ No memory leaks detected

## Security

☐ All RLS policies active

☐ HTTPS enforced

☐ Security headers configured

☐ No exposed API keys

☐ Input validation working

## Operations

☐ Monitoring alerts configured

☐ Error logging active

☐ Backup strategy in place

☐ Documentation complete

☐ Team trained

Document Version: 1.0

Last Updated: January 2024

Next Review: After Phase 1 completion